## story_map_v2
Use cases | Localisation |  |  | Navigation |  |  | Information
User tasks | Starting position | End position | Current position | Start navigation | Cancel navigation | Modify navigation | Receive information
Release 1 30/09 | Choose listed starting location | Choose listed end location |  | Text-based navigation | Finish navigation
Release 2 07/10 |  |  |  | Coronaproof navigation | Force stop navigation
Release 3 14/10 |  |  | Find current location | Select navigation type
Visual navigation (2D)
Backlog | Automate starting location |  |  | Utility-based navigation |  | Add multiple stops | Basic information
|  |  |  | AR navigation |  | Change destination | Utility information
"Did you know?"

## User story priority list
Must have | Show list of start locations
Show list of end locations
Find optimal path to destination
Show path in text format
Designate starting position
Designate finish position
Start navigation
Should have | Basic location info
2D visual navigation
End navigation
Change destination
Corona based directions
Automated localisation
Nice to have | Compass-based map rotation
Restroom hotkey
AR text-based directions
"Point me to the nearest free classroom"
Schedule integration
Find people on campus
Text-to-speech based directions
Alternate starting position
Multi-language support
Voice assist
Time tracking
Time estimates
Find location by room name
update location
Find optimized path to destination with constraints
AR arrow based directions